## Sheet1
| Oct. 1-29 | Oct. 30 | Nov. 10-25 | Nov. 27 | Dec. 5 | Dec. 1-23 | Jan. 13 | Jan. 20-31 | Feb. 1 | Feb. ? | Mar. 5 | March-April | May-Sept. | Sept. 3 | Sept.-Oct. | Dec. | Jan.-Mar. | Apr. | May. | June-Aug
Proposal | research & revising | revised draft done | fix revised draft | second draft done |  | submit??
Ethics | [5 empty] | drafting ethics | first draft done | fix draft | finish next draft | submit??
Recruiting | [12 empty] | start recruiting? |  |  | finish recruiting
Data collection | [15 empty] | start data collection | finish
> anthropometry data
> chart review
> IPS-HOOS
> PAQ-C PAQ-A
> accelerometry
> activity logs
Data analysis | [16 empty] | data analysis
Statistical analysis | [16 empty] | statistical analysis
Thesis | [16 empty] | first draft | second draft | final draft? | defence?
Finalize committee | [13 empty] | FINALIZE COMMITTEE
FIRST SEM CLASSES DONE |  |  |  |  | CLASSES DONE
SECOND SEM CLASSES DONE | [10 empty] | CLASSES DONE